## Case Study: E-Commerce Mobile App

### Background

A startup company, ShopEasy, wanted to build an e-commerce mobile application to allow customers to browse products, place orders, and track deliveries.
They needed a fast, flexible, and customer-centered approach to launch their app within 6 months

What model will we choose?
Agile

### Why did you choose your model?

As it’s Flexible and Customer-centered, and it’s needed to be launched within 6 months, a relatively short time.

🧩 Phases of your Model in the Project (how will you handle it):

Backlog: Create requirements and user stories

Sprint Planning: Plan the duration of the sprint, and choose the highest priority user stories to be implemented.

Development: Implementation of the user stories, along with daily stand-up meetings to inform other members of the current status and decide if we’ll need to make any changes.

Testing: Testing of the features implemented in this sprint.

Review: Discuss the items implemented in this sprint with the stakeholders.

Retrospective: Discuss how the sprint went with the team, what was wrong and what was good.

Deployment: Deploy the stories that are implemented and tested.

Re-iterate the whole Cycle

### 🗓️ Timeline Example:

Each sprint will be 2-4 weeks, feature selection depends on priorities.

- System Design, Backlog creation and foundation of the project, Technologies selection (4 weeks).

- Products browsing and filtering (2 weeks).

- Authentication & User Profile (2 weeks).

- Product details page (2 weeks).

- Cart functionality (2 weeks).

- Payment and Checkout, Order creation (4 weeks).

- Delivery Tracking, Notifications (2 weeks).

- Wishlist, favourites (2 weeks).

- Further testing, optimization and deployment (4 weeks).

Total Project Duration: 6 months

### Key Outcomes:

- MVP is released with the most important features.

- Low-Risk.

- Customer is always involved with us after each sprint.

### ⚠️ Challenges Faced

- Changing requirements all the time.

- Feedback can overload us by increasing the time.

- Many meetings can distract the developers and development time.

- Having a deadline can be stressful and risky.